{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["项目实施进度简表"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"项目实施进度简表","index":0,"n_rows":10,"n_cols":8,"rows_kept":10,"cut":false,"hidden":false,"merged":[[0,0,0,7],[1,0,1,2],[2,0,2,2],[1,3,1,7]]}
["项目实施进度简表"]
["项目名称",null,null,"xxx系统"]
["项目经理",null,null,"xxx","编写人","xxx","编写日期","2020-01-01"]
["序号","进度比例","阶段名称","预计开始时间","预计结束时间","工作内容","阶段成果物","负责人"]
[1,0.15,"需求阶段","2019-10-16","2019-10-30","1.需求调研\n2.需求分析\n3.编写《需求规格说明书》\n4.需求评审","1.《需求规格说明书》\n2.需求评审记录或会议纪要等"]
[2,0.1,"设计阶段","2019-10-31","2019-11-28","1.编写《系统功能设计说明书》\n2.编写《系统数据库设计说明书》\n3.编写《系统原型设计说明书》\n4.设计评审","1.《系统功能设计说明书》\n2.《系统数据库设计说明书》\n3.《系统原型设计说明书》\n4.设计评审记录或会议纪要等。"]
[3,0.35,"开发阶段","2019-11-29","2020-01-28","1.系统开发及关键技术攻关\n2.系统缺陷修复","系统代码"]
[4,0.1,"测试阶段","2019-12-10","2020-02-15","1.编写测试用例\n2.执行系统单元及集成测试\n3.编写《测试报告》\n4.编写《培训文档》\n5.编写《用户手册》\n6.编写《安装维护手册》","1.《测试用例》\n2.《测试报告》\n3.《培训文档》\n4.《用户手册》\n5.《安装维护手册》"]
[5,0.2,"实施阶段","2020-02-16","2020-03-24","1.用户现场实施上线\n2.用户培训\n3.用户验收","1.培训《签到表》\n2.《系统竣工报告》"]
[6,0.1,"维护阶段","2020-03-25","2020-03-25","对系统正式上线后进行定期或非定期的维护"]