{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["项目周报"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"项目周报","index":0,"n_rows":23,"n_cols":7,"rows_kept":23,"cut":false,"hidden":false,"merged":[[21,6,21,7],[22,6,22,7],[23,6,23,7],[24,6,24,7],[7,6,7,7],[8,6,8,7],[7,3,7,4],[8,3,8,4],[7,0,7,2],[8,0,8,2],[6,6,6,7],[6,0,6,2],[0,0,0,7],[1,1,1,7],[2,0,2,1],[2,6,2,7],[3,0,3,1],[3,6,3,7],[4,0,4,7],[5,0,5,2],[5,3,5,4],[5,6,5,7],[6,3,6,4],[9,0,9,7],[10,0,10,3],[10,4,10,7],[11,0,11,3],[11,4,11,7],[12,0,12,7],[13,0,13,3],[13,4,13,7],[14,0,14,3],[14,4,14,7],[15,0,15,3],[15,4,15,7],[16,0,16,3],[16,4,16,7],[17,0,17,3],[17,4,17,7],[18,0,18,7],[19,0,19,3],[19,4,19,5],[19,6,19,7],[20,0,20,3],[20,4,20,5],[20,6,20,7],[23,0,23,3],[24,0,24,3],[21,4,21,5],[22,4,22,5],[23,4,23,5],[24,4,24,5],[21,0,22,3]]}
["项目周报"]
["项目名称","XXX系统"]
["当前WBS文件版本",null,null,"项目经理","XXX","项目阶段","开发"]
["项目总体进度",null,0.5,"项目状态","进行中","起止时间","2020.1.1-2020.4.5"]
["本周工作内容"]
["任务描述",null,null,"成果物",null,"进度（%）","异常原因"]
["1. 系统测试、性能优化",null,null,"系统功能测试、性能优化",null,0.5]
[]
[]
["遇到的问题及解决方法"]
[" 工作量较大，工期紧张。"]
[" 现场尚没有完工，模型校正工作量较大，可能会造成项目延期"]
["需领导协调解决的问题和建议"]
[]
[]
[]
[]
[]
["下周工作计划"]
["任务描述",null,null,null,"成果物",null,"预期进度（%）"]
["1. 系统开发",null,null,null,"系统功能测试、性能优化",null,0.5]
["2. 系统部署",null,null,null,"系统部署"]
[{"$nulls":4},"接口开发"]